## Read Me
Udyami Kutumba — Fresh Implementation Plan
Prepared 11 September 2026, from an independent pass through the live codebase at D:\DigiNik\Apps\udyamikutumba. Every number in this workbook was pulled directly from the current files this session.
Method note | The on-device shell was unreachable this session (a known Windows-update mounting issue), so files were pulled into a working copy and searched there instead of running grep directly on the disk — same source files, same result.
The two ticket IDs | 963fb9ce-2cc8-41d7-b60e-d4293954e509 (notifications backend) and ead85da9-1d41-430e-9b71-13b98364c6b5 (API optimization) do not appear anywhere in the project folder — root, .scratch, scratch, or payloads. Every estimate here is built purely from what today's code shows. Share either ticket if it carries scope not visible in the app yet.
Team assumption | 2 Flutter developers working in parallel, plus a backend developer delivering the notification, role-revoke, and family-linking APIs alongside. Scale durations roughly inversely if the real team is smaller or larger.
AI-assisted coding | Every estimate in this workbook — Plan 1, Plan 2, and Plan 3 alike — already assumes AI-assisted coding (Claude/Gemini-style pair programming) for the engineering work. It is not a further discount on top of these numbers; it is baked into them. The 'AI Compression' tab shows what the same work would cost without that assistance.
Correction applied this revision | "Notifications — core system + push infrastructure" was re-priced down from 9–13 days to 1.5–3 days, per your note that a first working cut of this is largely boilerplate. Every total in this workbook has been recalculated with that change — see the Plan tabs and the Notification Detail tab for where the saved time was reallocated.
How to read the numbers | Min/Max columns are hand-entered estimates (blue text = input); Total rows are formulas (black text) that sum them, so if you adjust any input the totals recalculate automatically.
Tabs in this workbook
1. Current State — what the code shows today, per feature area
2. Notification Detail — the ~64 trigger types mapped to real screens, with time breakdown
3. AI Compression — with vs without AI-assisted coding
4. Plan 1 - Actual Effort — full engineering effort, AI-assisted, person-days
5. Plan 2 - 45 Day Plan — phased plan to ~25 Oct 2026, with what's still pending at day 45
6. Plan 3 - 11 Sep-10 Oct — status against the client's requested date, with what's pending after
7. Risks & Dependencies

## Current State
What today's code actually shows
Verified directly against the live files this session — not carried over from any earlier document.
Area | Verified state
Leads — Own (My Leads) | Built and wired (my_leads_screen.dart, 19.4 KB, no TODOs found): tabs for given/received leads, calls LeadAPI.getAllLeads(), navigates into LeadDetailScreen, links to passleadscreen.dart to create a new lead. This contradicts the "still needs doing" framing — functionally complete today, needs polish/edge cases, not a rebuild. Worth confirming in case a different "Own" requirement is intended.
Leads — B2B / B2C / Social Channel / Communication / UBN | Functionally live already via two paths: (1) lead_management_screen.dart (64 KB) is a real unified dashboard — fetches live counts from RequirementsAPI.getB2CRequirements/getB2BRequirements, LeadAPI, and CommunicationsAPI().getAllCampaigns(), and routes into fully-built screens (communications_screen.dart 28.9 KB, social_channels_screen.dart 14.8 KB + campaigns_screen.dart 44 KB, requirements_screen.dart 9.7 KB, the UBN/UCN subscription flow). (2) The five files that look like dedicated per-source screens (b2b/b2c/manual/social_media/ucn_management_screen.dart) are all 2 bytes and, confirmed by a project-wide search, imported and navigated to from nowhere in the app — dead scaffolding, not pending work. Matches what you said: these five are already done, in substance.
Leads — AI Leads | Two separate implementations exist side by side: (a) lead_detail_screen.dart genuinely calls LeadAPI.getMatchedLeads(userId) — a real GET /bni-lead/matched/{userId} call — and renders matches with proper loading/empty states. Wired in from member_leads_screen.dart and my_leads_screen.dart, so every lead detail already shows a live AI Leads section. This is the UBN-based passed-lead suggestion code you were thinking of. (b) ai_lead_gen_screen.dart is a separate, unwired screen with 2 hardcoded rows and a dead "Scan for new matches" button — confirmed never navigated to from anywhere in the app.
Notifications | notifications_screen.dart is a static list of exactly 9 hardcoded cards — no API client, no read/unread state, no per-module counts. main_screen.dart opens it from a plain bell icon with no badge at all. pubspec.yaml has no push package of any kind (firebase_messaging, flutter_local_notifications, etc. — none present) — push delivery itself doesn't exist yet either. swagger.json (parsed fresh: 269 paths / 274 operations / 42 tags) has no Notification tag. From-scratch build: frontend, push infrastructure, and backend.
Sector selection | SectorAPI (13 methods, all verified) already supports the 3-level flow end to end — getAllSubSubSectors(subSectorId) and createOther for all three levels exist and work. passleadscreen.dart is the one screen already using all of it, including a working "create Sector + Sub-Sector + Sub-Sub-Sector" dialog — the reference pattern. SectorAPI() is instantiated in 10 files total; only 4 have a real cascading Sector -> Sub-Sector dropdown needing the third level: signup_screen.dart, profile_screen.dart, create_sector_request_screen.dart, invite_to_ucn_screen.dart. The other 5 (sector_team_screen.dart, directory_screen.dart — simple string filters; sector_dashboard_screen.dart, my_sector_requests_screen.dart, sector_join_review_screen.dart — display/approve-reject only) don't need this change. ProfileDataModel has no sub-sub-category field yet, so a small model addition rides along.
Profile / family matching | UserModel has mobileNumber (the natural key for phone-based matching). ProfileDataModel.spouse is a plain free-text string — no phone number, no account reference, confirmed by reading the full model. No invite/link code exists anywhere. Net-new feature end to end: backend invite/link endpoints and a linked-account data model, plus the frontend invite flow, pending-invite state, accept flow, and the "tap spouse's card to see their business" view.
Primary/secondary address | The data already exists — homeAddress/homeLatitude/homeLongitude and businessDetails.businessAddress/latitude/longitude both live on the profile today — but no flag exists for "which is the public default." Geofencing is already confirmed business-only: member_map_screen.dart and geofence_screen.dart both read location strictly from biz['latitude']/biz['longitude'], so existing behavior needs no change — just an explicit rule that the toggle must not touch it.
API optimization | timed_http.dart wraps every raw http call with a stopwatch and an UNCONDITIONAL print of elapsed seconds — runs in every build, not just debug, itself worth fixing. 12 (not 11) print_*.js codegen scripts each inject extra DEV DEBUG lines into one specific screen to trace slow calls. A direct search of lib/core/api for cache/Hive found nothing — no caching, de-duplication, or pagination exists yet. The 28 files under lib/core/api contain 188 call sites, 20 of which are internal plumbing, leaving 168 real per-endpoint calls across the other 26 client files, plus 15+ more in feature-level clients outside core/api. Roughly 180–190 endpoints wired today against the 274 the backend exposes (about two-thirds) — higher coverage than a guess would suggest, but the optimization work itself hasn't started.
AI Leads recommendation
Build ONE consolidated screen, and leave the existing contextual section alone. Revive ai_lead_gen_screen.dart as the single "AI Leads" home, wired to the same getMatchedLeads(userId) call already proven working inside lead_detail_screen.dart — de-risked twice over. Keep the working section inside LeadDetailScreen exactly as it is. The matched-leads endpoint returns one ranked list with no source split, so it's naturally a single feed, not five; the accept flow can reuse passleadscreen.dart's existing auto-fill logic once, not five times; there's still no dedicated "dismiss" endpoint, so either repurpose updateLeadStatus with a new status value or add a small endpoint.

## Notification Detail
Notifications — the full sweep
Every feature folder in lib/features and every API tag in swagger.json, mapped to plausible trigger types.
# | Module (screens it maps to) | Trigger types | Count
1 | Feed / Posts (post_screen.dart, post_detail_screen.dart, my_posts_screen.dart) | new comment, new like, new follower, new post from someone you follow, post shared | 5
2 | Directory / digital card (directory_screen.dart, member_detail_screen.dart, cards_screen.dart) | connection request received, connection accepted, your card viewed | 3
3 | Roles & Circles (manage_roles_screen.dart, assembly_roles_screen.dart, circle_roles_screen.dart) | assigned to a role, assignment confirmed by admin, role changed/removed. NOTE: RoleAPI today only has assignRole/getAllRoles/getAllRoleUsers — no remove/revoke-role endpoint exists yet, so the "removed" trigger needs that endpoint built first. | 3
4 | Leads — Own + B2B/B2C/Social/UBN + AI (my_leads_screen.dart, lead_detail_screen.dart, lead_appeals_screen.dart) | lead assigned to you, lead status changed, appeal submitted/responded, lead converted, gratitude pending, new AI match found | 6
5 | Meetings & Face-to-Face (meetings_screen.dart, face_to_face_screen.dart, scan_attendance_qr_screen.dart) | meeting scheduled, reminder, rescheduled, cancelled, F2F request, F2F confirmed, attendance/QR check-in confirmed | 7
6 | Sector join requests (create_sector_request_screen.dart, sector_join_review_screen.dart) | submitted, endorsed, approved, rejected, new business tag created | 5
7 | Gratitude (gratitude_screen.dart, gratitude_history_screen.dart) | gratitude slip received, milestone reached | 2
8 | Hall booking & Guests (hall_coordinator_screen.dart, guests_screen.dart) | booking confirmed/rejected, guest invited, RSVP received, checked in | 4
9 | Membership, wallet & campaigns (ucn_subscription_screen.dart, recharge_coins_screen.dart, campaign_detail_screen.dart) | renewal due, payment received/failed, wallet low/recharged, campaign delivered/failed, financial summary ready | 6
10 | Jobs & applications (jobs_screen.dart, job_apply_screen.dart, my_application_sceen.dart) | new matching job posted, application received, application status changed, job post approved/rejected | 4
11 | Requirements — B2B/B2C matching (requirements_screen.dart, my_requirements_screen.dart) | new requirement matches your business, response received | 2
12 | UQueens, training & programmes (uqueens_screen.dart, training_screen.dart, childrens_programme.dart, prince_princess_programme.dart) | registration open, training reminder, certificate/milestone ready | 3
13 | Ward/Assembly/leaderboards (ward_screen.dart, leader_board_screen.dart, assembly_leaderboard_screen.dart) | ward rank changed, new member joined your ward, scorecard updated, points milestone reached | 4
14 | News (news_screen.dart, news_management_dashboard_screen.dart) | new news/announcement relevant to your ward/sector | 1
15 | Social channels & incidents (incidents_screen.dart, review_approvals_screen.dart, storage_screen.dart) | incident reported/resolved, content pending your review, storage limit approaching | 3
16 | Onboarding / profile (profile_screen.dart, signup_screen.dart) | profile approved/verified, missing-field reminder, family member linked (once profile-matching ships) | 3
17 | Surveys, referrals & system messages | survey available, referral bonus earned, important SMS/email delivered as in-app notice | 3
| Total distinct trigger types |  | 64
Time required, in its three genuinely different pieces
Piece | Min days | Max days | Notes
Core notification system (first working cut) | 1.5 | 3 | firebase_messaging/local-notification handling wired from zero, a live feed screen backed by one list endpoint, basic unread/read state, a bell badge. Re-priced down from an original 9-13 days per your note — largely boilerplate once the backend exposes even a minimal list endpoint. Per-module badges, a full settings screen, and deep-link routing into every trigger type are tracked in the row below.
Wiring all ~64 trigger types across 17 modules | 15 | 21 | Each type needs a backend event or client trigger, a card template, a deep link, and on-device verification. AI assistance speeds up writing the repetitive per-type code, but each type still has to be fired and checked on a device. The role-removal trigger can't be verified until the missing RoleAPI revoke endpoint exists.
Play Store internal/closed testing (elapsed) | 6 | 10 | Review queue + minimum real-tester soak period before production. Independent of trigger count or coding speed — Google's clock, not the dev team's. Can run in parallel with other work.
Total for notifications alone | 22.5 | 34 | 6-10 of this is elapsed waiting time that overlaps other work, not pure engineering time.

## AI Compression
Does AI-assisted coding change the numbers?
It compresses the mechanical, pattern-heavy parts by roughly 25-35%. It does NOT compress Play Store review/soak time, backend delivery schedules, family-linking UX judgment calls, or on-device verification of each notification trigger.
| Without AI assistance (person-days) | With AI-assisted coding (person-days)
Core engineering effort (all 6 feature areas) | 61-94 | 43-66
Play Store elapsed/waiting time (not compressible) | 6-10 | 6-10
Grand total (range) | 67-104 | 49-76
Both columns are lower than an earlier pass of this table, purely because the notification core-system line was corrected from 9-13 days down to 1.5-3 days — nothing else changed. Ranges are entered as text here because each side combines several independently-ranged line items from the Plan tabs; see those tabs for the underlying per-item formulas.

## Plan 1 - Actual Effort
Plan 1 — Actual effort needed
AI-assisted, sequential person-days. This is the honest total engineering effort for all six feature areas if it were done as pure sequential effort with no parallelization.
Feature | Min days | Max days
Leads — Own: polish, edge/empty states (already built, not a rebuild) | 1 | 2
Leads — B2B/B2C/Social/Communication/UBN: delete the 5 orphaned stub files, confirm existing dashboard + full screens cover the need | 0.5 | 1
Leads — AI Leads: consolidated screen wired to getMatchedLeads, accept/dismiss, keep the existing contextual section | 3 | 5
Notifications — core system + push infrastructure (REVISED per your note: was 9-13 days) | 1.5 | 3
Notifications — wiring ~60-65 trigger types | 15 | 21
Notifications — Play Store testing cycle (elapsed, parallelizable) | 6 | 10
Profile matching — family/spouse linked accounts, invite, tap-through, multi-member | 9 | 13
Primary/secondary address toggle + updating ~4 display surfaces | 3 | 5
API optimization — gate/remove always-on debug prints, then cache/paginate/de-dupe across ~180-190 wired calls | 7 | 11
Sector sub-sub-sector rollout — 4 confirmed screens + small model field | 3 | 5
Total (person-days, AI-assisted) | 49 | 76
With 2 developers running independent tracks in parallel and backend delivering notifications/role-revoke/family-link APIs on its own schedule, this compresses to roughly 29-45 calendar days before final QA and release — about 3-5 days tighter than before this revision, purely from the notification core-system correction.

## Plan 2 - 45 Day Plan
Plan 2 — 45 calendar days
Target finish approx. 25 October 2026. AI-assisted throughout — see Read Me tab. Tight scope: both developers fully dedicated, backend delivers notification + family-link + role-revoke APIs on schedule, Play Store beta cycle overlapped with the final QA week.
Phase | Days | Deliverables
Phase 1 | 1-7 | Sector sub-sub-sector rollout (4 screens); primary/secondary address toggle + display logic; delete the 5 orphaned lead-management stubs; notifications core system + push infrastructure built (now a 1.5-3 day item, so it lands early); backend starts on notification, role-revoke, and family-link APIs in parallel.
Phase 2 | 6-16 | Leads: Own finalized, AI Leads consolidated screen wired to getMatchedLeads.
Phase 3 | 14-32 | Notifications: trigger-type wiring, now with 3-5 extra days freed up by the core-system correction to push toward the higher-priority ~35-40 of the ~64 types; profile family/spouse matching built (invite, link, tap-through).
Phase 4 | 30-40 | Remaining notification trigger types wired to reach the full ~64; API optimization pass across the ~180-190 wired calls.
Phase 5 | 38-45 | Full regression QA, Play Store closed-testing submission and monitoring, bug-fixing, release.
What's realistically still pending at day 45, even in this plan
This is the "complete by 45 days" target, so it's built to reach release — but two genuine risk points remain: (1) the ~64-notification catalogue — if any trigger's backend event slips, that type carries past day 45; and (2) the Play Store review queue itself, which runs on Google's schedule and can push the actual public release a few days past day 45 even if every build task inside the team's control finishes on time. A second API-optimization pass is also expected once the new notification/role-revoke/family-link endpoints land — that's follow-on work by design, not a miss on this plan.
Same feature-by-feature breakdown as Plan 1, checked against the 45-day capacity
Plan 2 is framed as reaching full release, so every feature's full effort from Plan 1 has to fit inside the 45 days. The Min/Max columns below are live links to the Plan 1 tab (green = cross-sheet link), not re-typed numbers.
Feature |  |  | Min days | Max days
Leads — Own: polish, edge/empty states (already built, not a rebuild) |  |  | 1 | 2
Leads — B2B/B2C/Social/Communication/UBN: delete the 5 orphaned stub files, confirm existing dashboard + full screens cover the need |  |  | 0.5 | 1
Leads — AI Leads: consolidated screen wired to getMatchedLeads, accept/dismiss, keep the existing contextual section |  |  | 3 | 5
Notifications — core system + push infrastructure (REVISED per your note: was 9-13 days) |  |  | 1.5 | 3
Notifications — wiring ~60-65 trigger types |  |  | 15 | 21
Notifications — Play Store testing cycle (elapsed, parallelizable) |  |  | 6 | 10
Profile matching — family/spouse linked accounts, invite, tap-through, multi-member |  |  | 9 | 13
Primary/secondary address toggle + updating ~4 display surfaces |  |  | 3 | 5
API optimization — gate/remove always-on debug prints, then cache/paginate/de-dupe across ~180-190 wired calls |  |  | 7 | 11
Sector sub-sub-sector rollout — 4 confirmed screens + small model field |  |  | 3 | 5
Total (person-days, AI-assisted) — should equal Plan 1's total |  |  | 49 | 76
Capacity check: 2 developers x 45 days is approx. 90 person-days of raw capacity (before counting backend, which runs its own track) — comfortably above the 76-day worst case above. That headroom (roughly 14-41 person-days) is what Phase 5's QA / bug-fixing / testing-monitoring time draws from.

## Plan 3 - 11 Sep-10 Oct
Plan 3 — 11 September to 10 October
The client's requested date; approx. a 29-30 day window. AI-assisted throughout. Because leads needed far less rebuilding than the "needs to do" list assumed, and the notification core-system estimate is now corrected down to 1.5-3 days (freeing several more days for trigger-type wiring), this window is more workable than it would otherwise look.
Status by 10 Oct | Item
Done | Sector sub-sub-sector rollout across all 4 confirmed screens
Done | Primary/secondary profile address switching
Done | Leads — Own (My Leads) polished; the 5 orphaned stub files removed and the existing B2B/B2C/Social/Communication/UBN access points confirmed
Done | Leads — AI Leads consolidated screen live, wired to the real getMatchedLeads endpoint
Done | Notifications core system live (feed, read/unread, badges, push registration, deep links) — built in the first few days rather than the first two weeks — plus roughly the top 30-35 of the ~64 trigger types (up from ~25-30 before the correction, since the days saved on the core system roll straight into trigger wiring)
Partial | Profile family matching — invite + linking flow likely built for spouse; multi-family-member support and full tap-through polish likely carries over
Pending / carried over past 10 Oct | Remaining ~29-34 notification trigger types (including anything depending on the not-yet-built role-revoke endpoint), the full API optimization pass, Play Store closed-testing submission, full multi-member family-matching polish
In short: this window comfortably covers the two smaller self-contained items (sector rollout, address switching), the leads cleanup and AI Leads screen, and — now that the core system is a fast build rather than a two-week one — a notification system that's not just live but meaningfully populated. The remaining notification types, the complete family-matching feature, and the API optimization pass are what's genuinely pending past 10 October, and need the additional 8-17 days captured in Plan 2 to close out.
Same feature-by-feature breakdown as Plan 1, split into what fits inside the window and what doesn't
Each row's two halves add back up to that feature's Plan 1 total. "Days done" columns are entered directly from the assessment above; "Days pending" columns are formulas: Plan 1's total for that feature minus the days done — so they can never silently drift out of sync with Plan 1.
|  | Feature | Done: Min | Done: Max | Pending: Min | Pending: Max
|  | Leads — Own: polish, edge/empty states (already built, not a rebuild) | 1 | 2 | 0 | 0
|  | Leads — B2B/B2C/Social/Communication/UBN: delete the 5 orphaned stub files, confirm existing dashboard + full screens cover the need | 0.5 | 1 | 0 | 0
|  | Leads — AI Leads: consolidated screen wired to getMatchedLeads, accept/dismiss, keep the existing contextual section | 3 | 5 | 0 | 0
|  | Notifications — core system + push infrastructure (REVISED per your note: was 9-13 days) | 1.5 | 3 | 0 | 0
|  | Notifications — wiring ~60-65 trigger types | 7 | 11 | 8 | 10
|  | Notifications — Play Store testing cycle (elapsed, parallelizable) | 0 | 0 | 6 | 10
|  | Profile matching — family/spouse linked accounts, invite, tap-through, multi-member | 5.5 | 8.5 | 3.5 | 4.5
|  | Primary/secondary address toggle + updating ~4 display surfaces | 3 | 5 | 0 | 0
|  | API optimization — gate/remove always-on debug prints, then cache/paginate/de-dupe across ~180-190 wired calls | 0 | 0 | 7 | 11
|  | Sector sub-sub-sector rollout — 4 confirmed screens + small model field | 3 | 5 | 0 | 0
|  | Total | 24.5 | 40.5 | 24.5 | 35.5
So of the 49-76 person-days in Plan 1, roughly the "Done" total above actually lands inside the 11 Sep-10 Oct window, and the "Pending" total carries into the remainder of Plan 2 (days 30-45) — the same split shown qualitatively in the status table above, now quantified and formula-linked to Plan 1.

## Risks & Dependencies
Dependencies and risks worth flagging to the client
Notifications and family-invite both need backend endpoints that don't exist yet, and role-removal notifications specifically need a new RoleAPI revoke/remove endpoint that isn't there today either — every plan above assumes backend delivers these in parallel and on schedule; a slip there pushes the matching frontend milestones directly. AI Leads is lower-risk than a first read suggests: the exact fetch/render pattern (getMatchedLeads -> card list) is already shipping today inside LeadDetailScreen, so the consolidated screen is proven, not speculative — the remaining work is the screen itself, the accept/dismiss flow, and (if "dismiss" needs its own status) a small backend addition. The Play Store closed/internal testing track carries elapsed time outside the team's control and is the tightest point in Plan 2's timeline. Finally, the 274-operation backend surface (42 modules) against roughly 180-190 wired calls today means the app's API surface keeps growing as these six features land — the optimization pass above is scoped against today's baseline, so expect a second optimization pass once the new notification, role-revoke, and family-linking endpoints go live.