## Overview
Udyami Kutumba — New Features Implementation Plan
Prepared | 11 September 2026
Plan start date (Day 1) | 2026-09-11
Team assumption | 2 Flutter developers full-time in parallel, plus 1 backend developer handling notification + family-link APIs in parallel (existing backend ticket).
AI-assisted development | Yes — estimates below assume Claude/Gemini-style AI coding assistants are used for repetitive build work (CRUD screens, API wiring, refactors). This compresses pure coding effort by ~25-35% but does NOT compress Play Store review/soak time, backend delivery schedules, or on-device testing of each notification trigger.
Tickets referenced by client | 963fb9ce-2cc8-41d7-b60e-d4293954e509 (notifications, backend) and ead85da9-1d41-430e-9b71-13b98364c6b5 (API optimization). Neither ID, nor any chat/ticket export containing them, exists anywhere in the local project folder (lib/, .scratch, scratch, payloads all checked) — all estimates come from direct review of the app codebase and swagger.json.
Backend API surface (swagger.json) | 274 documented endpoints (269 paths) across 42 modules — confirmed by parsing the file directly.
Client-side endpoints currently wired | ~125-130 of the 274, across 28 API client files in lib/core/api.
How to use this workbook | Sheet 2 shows what the app has today, verified file-by-file. Sheet 3 is the notifications deep-dive (the specific question asked). Sheet 4 is the raw AI-assisted engineering effort per feature ('Actual Days'), independent of calendar compression. Sheets 5-6 turn that effort into the two calendar plans requested: 45 days, and what fits between 11 Sep and 10 Oct 2026.

## Current State
Current State — Verified Directly Against the Codebase
Area | Current state (file names / counts verified directly)
Leads — Own (My Leads) | Built and functional. my_leads_screen.dart + LeadAPI with 8 verified endpoints: createLead, getLeadsById, getAllLeads, updateLeadStatus, getCompletedLeadsByUser, getConvertedLeadsByUser, getFreeMemberLeads, getPaidMemberLeads. Needs final polish, not a rebuild.
Leads — AI Leads | UI shell only. ai_lead_gen_screen.dart read in full: 2 hardcoded rows (Priya Shetty, Suresh Rao), 'Scan for new matches' button has an empty onPressed. UPDATED: LeadAPI already has a wired getMatchedLeads(userId) -> GET /bni-lead/matched/{userId} endpoint. The screen just isn't calling it yet. Backend risk for this item is now low; remaining work is frontend (consolidated screen + accept/dismiss flow).
Leads — B2B/B2C/Social/Communication/UCN management | 5 dedicated management screens confirmed empty: b2b_management_screen.dart, b2c_management_screen.dart, manual_management_screen.dart, social_media_management_screen.dart, ucn_management_screen.dart — each exactly 2 bytes on disk. Filtering by type already exists inside lead_management_screen.dart.
Notifications | notifications_screen.dart read in full: exactly 9 hardcoded NotificationItem cards, no read/unread state, no API. swagger.json (parsed directly) has zero 'Notification' tagged endpoints among its 42 modules — this is a from-scratch build on both frontend and backend.
Sector selection | SectorAPI (13 methods) already supports the 3-level flow (getAllSubSubSectors, createOther). UPDATED: passleadscreen.dart ('Pass a Lead') already fully implements Sector -> Sub-Sector -> Sub-Sub-Sector end to end, including a working 'create all 3 levels' dialog - this is the reference template to copy. Confirmed by grep: exactly 7 screens still use the 2-level flow only - signup_screen.dart, profile_screen.dart, create_sector_request_screen.dart, my_sector_requests_screen.dart, sector_team_screen.dart, sector_join_review_screen.dart, sector_dashboard_screen.dart. ProfileDataModel also needs a new businessSubSubCategory-equivalent field.
Profile / family matching | user_profile_model.dart read in full: ProfileDataModel already has spouse, children, familyCount fields, plus homeAddress/officeAddress and separate lat/long for home. No linked-account model, invite mechanism, or bidirectional link exists. New feature end to end.
Primary/secondary address | Underlying data already exists (home address+coords, business/office address+coords). Missing: default-display toggle logic, and the explicit rule that geofencing/Member Map keeps business location regardless of the toggle.
API optimization | 11 debug-print scripts in project root (print_geo_all.js, print_roles.js, print_search.js, print_selects.js, print_check_profile.js, print_nearby2.js, print_load_map.js, print_loc2.js, print_tabs.js, print_web_map.js, print_area_filters.js) have patched 11 screens with console logging — diagnostic only, no caching/pagination/de-dup/trimming done. lib/core/api has 28 client files. Backend: 274 endpoints/42 modules (swagger.json, parsed directly: 269 paths, 274 operations, 42 tags). App wires ~125-130 of those.

## Notifications Deep-Dive
Notifications — Every Module Mapped, With a Real Count
# | Module | Trigger types needed | Count
1 | Feed / Posts | New comment, new like, new follower, new post from someone you follow, post shared | 5
2 | Directory / Networking | Connection request received, connection accepted, your profile/digital card viewed | 3
3 | Roles & Circles (Ward/Circle/Assembly/Coordinator) | Assigned to a role, role assignment confirmed by admin, role changed/removed (kept distinct from assignment so a member who is NOT removed keeps receiving role-scoped notices) | 3
4 | Leads (Own/B2B/B2C/Social/UCN + AI) | Lead assigned to you, status changed, appeal submitted/responded, converted, gratitude pending, AI-suggested match found | 6
5 | Meetings & Face-to-Face | Scheduled, reminder, rescheduled, cancelled, F2F request received, F2F confirmed, attendance/QR check-in confirmed | 7
6 | Sector join requests | Submitted, endorsed, approved, rejected, new business tag created | 5
7 | Gratitude | Gratitude slip received, gratitude milestone reached | 2
8 | Hall booking & Guests | Booking confirmed/rejected, guest invited, guest RSVP received, guest checked in | 4
9 | Membership, wallet & campaigns | Renewal due, payment received/failed, wallet low/recharged, campaign delivered, campaign failed, wallet/financial summary ready | 6
10 | Jobs & applications | New matching job posted, application received, application status changed, job post approved/rejected | 4
11 | Requirements (B2B/B2C matching) | New requirement matches your business, requirement response received | 2
12 | UQueens, training & programmes | Event registration open, training reminder, programme certificate/milestone ready | 3
13 | Ward/Assembly/leaderboards | Ward rank changed, new member joined your ward, scorecard updated, points milestone reached | 4
14 | News & announcements | New news/announcement relevant to your ward/sector | 1
15 | Onboarding / profile | Profile approved/verified, missing-field reminder, family member linked (once profile-matching ships) | 3
16 | Surveys, referrals & system messages | Survey available, referral bonus earned, important SMS/email delivered as in-app notice | 3
Total distinct trigger types
Time required (3 components):
| Component | Days | Why
| Core system (live feed, read/unread, badges, settings, deep links, push registration) | 8-11 days | AI-assisted scaffolding of repeated list/badge/settings UI
| Wiring all ~60 trigger types across 16 modules | 14-20 days | Each type still needs an on-device fire-and-verify pass regardless of coding speed
| Play Store internal/closed testing track | 6-10 days (elapsed) | Google's review queue + minimum tester soak period — independent of trigger count
Total for notifications alone: roughly 28-41 days, of which 6-10 days is elapsed waiting time that can run in parallel with other feature work.

## Actual Days Plan
Plan 1 — Actual Days Needed (AI-Assisted Engineering Effort, No Calendar Compression)
# | Feature | Min days (no AI) | Max days (no AI) | Min days (AI-assisted) | Max days (AI-assisted) | Notes
1 | Leads — Own: polish, edge cases, empty/error states | 2 | 3 | 1 | 2 | Already ~90% built; finishing touches only.
2 | Leads — AI Leads: consolidated screen wired to the real matched-leads endpoint, accept/reject/pass | 6 | 9 | 4 | 6 | Backend matching endpoint (getMatchedLeads) already exists and is wired client-side - lower risk than first assumed. Remaining work: one consolidated screen (not 5 separate ones - see Follow-up Notes sheet), real source badges, accept/dismiss flow.
3 | Leads — 5 management screens (B2B, B2C, Social, Communication, UCN) | 18 | 25 | 12 | 17 | 5 empty stubs today; full list/filter/assign/status/bulk-action dashboards needed. Highly repetitive — good AI-compression candidate.
4 | Notifications — core system + ~60 trigger types (see Deep-Dive sheet) | 20 | 28 | 14 | 20 | Core system compresses well; per-trigger wiring is bounded by on-device verification, not coding speed.
5 | Notifications — Play Store testing cycle | 6 | 10 | 6 | 10 | Elapsed/waiting time (review queue + tester soak) — cannot be compressed by AI tooling.
6 | Profile matching — family/spouse linked accounts, invite, tap-through | 10 | 15 | 8 | 12 | New feature end to end; UX/backend coordination limits AI compression.
7 | Primary/secondary address toggle + display logic | 4 | 6 | 3 | 4 | Address/lat-long fields already exist; UI + display-logic wiring only.
8 | API optimization pass across ~125-130 endpoints / 28 files | 12 | 18 | 8 | 13 | Repetitive refactor across many similar files — strong AI-compression candidate.
9 | Sector sub-sub-sector rollout to the 7 confirmed remaining screens (using passleadscreen.dart as the template) | 6 | 9 | 4 | 6 | Backend already supports 3-level flow; UI catch-up only.
Total (person-days)
With 2 developers running independent tracks in parallel (plus backend on its own ticket), the AI-assisted total compresses to roughly 40-55 calendar days before QA/release — why Plan 2 (45 days) below is tight, not padded.

## 45-Day Plan
Plan 2 — 45 Calendar Days (Target Finish ~25 Oct 2026)
Phase | Start Day | End Day | Start Date | End Date | Duration (d) | Deliverables
Phase 1 | 1 | 9 | 2026-09-11 | 2026-09-19 |  | Sector sub-sub-sector rollout across all screens; primary/secondary address toggle + display logic built. Backend proceeds in parallel on notification + family-link APIs.
Phase 2 | 7 | 20 | 2026-09-17 | 2026-09-30 |  | Leads: Own finalized, AI Leads fully wired. Notifications core system built (live feed, read/unread, badges, deep links) plus the highest-priority ~30 of the ~60 trigger types.
Phase 3 | 18 | 32 | 2026-09-28 | 2026-10-12 |  | Leads: all 5 management screens built (B2B, B2C, Social Channel, Communication, UCN). Profile family/spouse matching built (invite, bidirectional link, tap-through).
Phase 4 | 30 | 39 | 2026-10-10 | 2026-10-19 |  | Remaining notification trigger types wired to reach the full ~60. Full API optimization pass across the ~125-130 wired endpoints.
Phase 5 | 38 | 45 | 2026-10-18 | 2026-10-25 |  | Full regression QA, Play Store closed-testing submission and monitoring, bug-fixing, release.
Assumes both developers fully dedicated with no other work, backend delivers notification + family-link APIs on schedule, and the Play Store beta cycle overlaps the final QA week (the tightest point in this plan).

## Sept 11 - Oct 10 Plan
Plan 3 — 11 Sep to 10 Oct 2026 (30-Day Window, Client's Requested Date)
Window start | 2026-09-11
Window end | 2026-10-10
Window length (days)
Note | This window is shorter than Plan 2 (45 days), so full scope will not be complete by 10 Oct with a 2-developer (+1 backend) team, even with AI-assisted coding.
Item | Status by 10 Oct | Notes
Sector sub-sub-sector rollout across all screens | Done | Small, well-contained item; backend API already ready.
Primary/secondary profile address switching | Done | Underlying address fields already exist; mostly UI + display logic.
Leads — Own (My Leads) finalized | Done | Already ~90% built before this plan started.
Leads — AI Leads fully wired | Done | Assumes the backend AI-matching endpoint is ready within this window.
Notifications — core system live (feed, read/unread, badges, deep links) | Done | Plus roughly the top 20-25 highest-value trigger types out of ~60 (see Deep-Dive sheet).
Leads — management screens (B2B, B2C, Social, Communication, UCN) | Partial | Realistically 2 of 5 built (e.g. B2B and B2C); the other 3 carry over past 10 Oct.
Profile family matching (invite, link, tap-through, multi-member) | Partial | Invite + linking flow likely built; multi-family-member support and tap-through polish likely carries over.
Notifications — remaining ~35-40 trigger types | Carried over | Only the top-priority subset fits in this window.
API optimization pass | Carried over | Only continued diagnostics, not a completed optimization sweep.
Play Store closed/internal testing submission | Carried over | Not realistically reached by 10 Oct given feature completion timeline.
In short: 30 days covers the two smaller, self-contained items plus the leads baseline and a working (partially populated) notifications system. The heavier items — all 5 lead-management screens, the full ~60-notification catalogue, family matching at full scope, and the API optimization pass — need the additional 15-25 days captured in Plan 2 (45-Day Plan sheet).

## Follow-up Notes
Follow-up Findings — Same-Day Second Pass (AI Leads screen design + rollout recheck)
Question asked | Should AI Leads be one consolidated screen, or suggestions spread across each of the 5 lead-type screens (UBN, B2B, B2C, Social Channel, Communication)?
Recommendation | One consolidated screen (keep ai_lead_gen_screen.dart as the single home). The real backend endpoint (GET /bni-lead/matched/{userId}) returns one ranked list, not five separate ones by source - splitting it across 5 screens would mean 5x the accept/reject logic for no user benefit. Each suggested lead shows a source badge (UBN / B2B / B2C / Social / Communication) using the badge UI already stubbed in the screen; Accept reuses the category auto-fill pattern already built in passleadscreen.dart to create a real lead in the right bucket.
New finding: AI Leads backend | LeadAPI.getMatchedLeads(userId) -> GET /bni-lead/matched/{userId} already exists and is wired in the Flutter client. ai_lead_gen_screen.dart does not call it yet (still 2 hardcoded rows). This removes the earlier assumption that AI Leads was blocked on a backend matching endpoint - it exists today.
New finding: Sector sub-sub-sector reference | passleadscreen.dart ('Pass a Lead') already fully implements Sector -> Sub-Sector -> Sub-Sub-Sector, including a working 'create all 3 levels' dialog. This is a proven, working pattern in the same codebase - the rollout to the remaining screens is a copy-the-pattern job, not new design work.
New finding: exact rollout list | Grepped every file calling SectorAPI() directly. Still 2-level only: signup_screen.dart, profile_screen.dart, create_sector_request_screen.dart, my_sector_requests_screen.dart, sector_team_screen.dart, sector_join_review_screen.dart, sector_dashboard_screen.dart (7 screens). ProfileDataModel has no businessSubSubCategory-equivalent field yet - needs a small model addition alongside the UI work.
Net effect on the plan | No change to the day ranges in Plan 1/2/3 - the AI Leads and sector-rollout items were already estimated assuming this level of complexity. What changed is confidence: AI Leads backend risk is now confirmed low (endpoint exists), and the sector rollout has a working reference to copy instead of building the 3-level UX from scratch.